## Sheet1
Task | Start Date | Days to Complete
Design Levels and Characters | 2019-02-13 | 7
Storyboarding | 2019-02-20 | 10
Retexture Characters | 2019-02-27 | 4
Rigging Characters | 2019-03-06 | 10
Retexture Backgrounds | 2019-03-20 | 4
Level-Character Collision | 2019-03-27 | 13
Design Menu / Interface | 2019-04-03 | 7
Add more Levels | 2019-04-10 | 8
QA / Testing | 2019-04-17 | 10
Search for Issues / Bugs | 2019-04-24 | 8